## Financial Proj
Housing |  | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 535000 | 775000 | 3175000 | 3385000 | 4300000
Quarterly Projection |  | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 85000 | 240000 | 2400000 | 210000 | 4090000
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 464460.4 | 549090.42 | 792154.91 | 3335037.59 | 3549160.43 | 3642450.43 | 3600437.54
Actual Quarterly Expend (from QPRs) | 0 | [5 empty] | 464460.4 | 84630.02 | 243064.49 | 2542882.68 | 214122.84 | 93290 | -42012.89
Program expenses will be incurred prior to project completion.
Infrastructure |  | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022
Projected Expenditures | 0 | 0 | 0 | 340000 | 570000 | 570000 | 1570000 | 5570000 | 9870000 | 28354625 | 33408609 | 38258609 | 43819119 | 45463936 | 47108753 | 48753570 | 50398387 | 52043204 | 53688021 | 54021394 | 54354767 | 54688140 | 55021513 | 55354886 | 55688259 | 56021632 | 56355005 | 56688378 | 57021751 | 57355124 | 57688497 | 58021870
Quarterly Projection | 0 | 0 | 0 | 340000 | 230000 | 0 | 1000000 | 4000000 | 4300000 | 18484625 | 5053984 | 4850000 | 5560510 | 1644817 | 1644817 | 1644817 | 1644817 | 1644817 | 1644817 | 333373 | 333373 | 333373 | 333373 | 333373 | 333373 | 333373 | 333373 | 333373 | 333373 | 333373 | 333373 | 333373
Actual Expenditure | 0 | 0 | 0 | 564286.16 | 564286.16 | 564286.16 | 3780406.49 | 7381896.22 | 17520805.24 | 25326915.6 | 37249434.56 | 39994594.5 | 44076718.13
Actual Quarterly Expend (from QPRs) | 0 |  | 0 | 564286.16 | 0 | 0 | 3216120.33 | 3601489.73 | 10138909.02 | 7806110.36 | 11922518.96 | 2745159.94 | 4082123.63
Program expenses will be incurred prior to project completion.
Planning & Admin |  | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 250000 | 367000 | 487000 | 637000 | 667000 | 667000 | 697000 | 700118.16 | 703236.32 | 706354.48 | 709472.64 | 712590.8 | 715708.96 | 718827.12 | 721945.28 | 725063.44 | 728181.6 | 731299.76 | 734417.92 | 737536.08 | 740654.24 | 743772.4 | 746890.56 | 750008.72 | 753126.88
Quarterly Projection | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 150000 | 117000 | 120000 | 150000 | 30000 | 0 | 30000 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16 | 3118.16
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 163305.74 | 176926.32 | 302512.84 | 512360.91 | 543877.97 | 543877.97 | 497482.92
Actual Quarterly Expend (from QPRs) | 0 | [5 empty] | 163305.74 | 13620.58 | 125586.52 | 209848.07 | 31517.06 | 0 | -46395.05
Total Expenditures |  | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 04/2019
Projected Expenditures | 0 | 0 | 0 | 340000 | 570000 | 570000 | 1670000 | 6270000 | 10772000 | 29616625 | 39700609 | 47661119 | 49545936 | 52108871.16 | 49456806.32 | 51104741.48 | 52752676.64 | 54400611.8 | 63075000
Quarterly Projection | 0 | 0 | 0 | 340000 | 230000 | 0 | 1100000 | 4600000 | 4502000 | 18844625 | 7603984 | 5090000 | 9650510 | 1674817 | 1647935.16 | 1647935.16 | 1647935.16 | 1647935.16 | 1647935.16
Actual Expenditure | 0 | 0 | 0 | 564286.16 | 1128572.16 | 0 | 4972458.63 | 8672198.96 | 19179758.99 | 29738600.1 | 41906758.96 | 44745208.9 | 48738924.59
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 564286.16 | 564286 | 0 | 3843886.47 | 3699740.33 | 10507560.03 | 10558841.11 | 12168158.86 | 2838449.94 | 3993715.69

## Performance Proj
Construction of New Housing |  | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Quarterly Projection) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0
Homeownership Assistance |  | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0
Residential Rehab and Reconstruction |  | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
# of Housing Units (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
# of Housing Units (Populated from QPR Reporting) | 0
Public Facilities |  | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017
Projected Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Public Facilities (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Public Facilities (Populated from QPR Reporting) | 0
Quarterly Projections by Activity Type:
Acquisition, construction,reconstruction of public facilities
# of Public Facilities | 0
Construction/reconstruction of water lift stations
# of Public Facilities | 0
Construction/reconstruction of water/sewer lines or systems
# of Public Facilities | 0
Dike/dam/stream-river bank repairs
# of Public Facilities | 0
Rehabilitation/reconstruction of public facilities
# of Public Facilities | 0
Economic Development |  | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Projected Jobs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Jobs Created/Retained (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Jobs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Jobs Created/Retained (Populated from QPR Reporting) | 0
# of Permanent Jobs Created | 0
# of Permanent Jobs Retained | 0
Public Infrastructure |  | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016 | 4/2016 | 7/2016 | 10/2016 | 1/2017 | 4/2017 | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019
Projected Linear Feet of Public Improvements | 0 | 0 | 0 | 0 | 0 | 1700 | 3200 | 5200 | 7200 | 9700 | 12200 | 14254 | 14254 | 32954 | 35454 | 37454 | 39954 | 40954 | 41354
# of Linear Feet of Public Improvements (Quarterly Projection) |  | 0 | 0 | 0 | 0 | 1700 | 1500 | 2000 | 2000 | 2500 | 2500 | 2054 | 0 | 18700 | 2500 | 2000 | 2500 | 1000 | 400
Actual Linear Feet of Public Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2054 | 0
# of Linear Feet of Public Improvements (Populated from QPR Reporting) | 0 | [10 empty] | 2054 | 0
Quarterly Projections by Activity Type:
Construction/reconstruction of water/sewer lines or systems
# of Linear Feet of Public Improvements | 0 |  |  |  |  | 1700 | 1500 | 2000 | 1700 | 1700 | 1500 | 2000 | 0 | 2700 | 1200 | 879 | 1500 | 742 | 1000
Dike/dam/stream-river bank repairs | [11 empty] | 2054 | 0
# of Linear Feet of Public Improvements | 0
Rehabilitation/reconstruction of a public improvement
# of Linear Feet of Public Improvements | 0 | [8 empty] | 500 | 900 | 700 | 1000 | 700 | 1000 | 1000 | 1000 | 1879 | 1300